## Slide 1: In 12 weeks, we prove the gain on the bottleneck line
OUR 12 WEEKS
1
Diagnosis
2–4 wks
W1–W4
Charter signed, baseline agreed
2
Tech proof
6–12 wks
W4–W12
Named users, gain measured
3
Scaling
3–9 months
M4–M12
All lines, owned by IT
4
Anchoring
Ongoing
Line by line
Holds without us
Notes: A four-stage method. Our 12 weeks cover Diagnosis and Tech proof. Each stage ends on an exit criterion the sponsor can see. We anchor each line before moving to the next. The whole site follows in 6 to 9 months.

## Slide 2: 4 projects in parallel, a go or stop every 4 weeks
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
Scheduling
Capacity: direct
Diagnosis
Tech proof
Product quality
Capacity: direct
Diagnosis
Tech proof
Quality release
Cash and service
Diagnosis
Tech proof
Time to market
Growth
Diagnosis
Only if go at W4
Go / stop W4
Go / stop W8
Go / stop W12
Some initiatives will fail: stopping a project is a result
Notes: Scheduling and product quality carry the capacity gain. Quality release mostly brings cash, counted once, and service. Time to market moves to tech proof only if the W4 gate justifies it. Some initiatives will fail: stopping a project is a result, written up like a gain.

## Slide 3: Every gate has a kill criterion, agreed today
Project | Stop at W4 if… | Stop at W8 if…
Scheduling | Changeovers explain little of the capacity loss | Backtest gain below the agreed threshold
Product quality | Scrap and deviations weigh little in OEE | No drop in deviations on the pilot line
Quality release | Review is not the release bottleneck | One critical anomaly missed
Time to market | Lead time sits mostly outside the plant (R&D, regulatory) | Becomes a recommendation
Rule: failing the same gate twice means we stop. Thresholds set with the sponsor.
Notes: Thresholds are set with the sponsor and the controller. The criteria are read out at every steering committee. Failing the same gate twice is a decision to stop.

## Slide 4: A gain counts when your controller computes it without us
Bottleneck line
is where capacity is measured, at normalized mix
Baseline signed in W1 by the controller
Freed capacity
Sold?
Yes
Contribution margin
No
Avoided costs only
To prove in W2: order book and lost sales
Notes: The capacity gain is measured on the bottleneck line: an hour gained elsewhere adds no batch. Freed capacity is worth money only if it is sold. Question for the committee: what is the order book against demonstrated capacity? Export stockouts suggest yes; to be proven. The cash from quality release stock counts once. The baseline and the gains protocol (metric, formula, source, normalization, cadence, sign-off threshold) are signed in W1.

## Slide 5: AI proposes, your teams decide
Shadow
Runs alongside the team
Co-pilot
Every change has a reason
Default
The team can object
Autonomous by class
Small, known decisions
12 weeks
Batch release: always the qualified person
GOVERNANCE
Weekly
Ops review, 30 min
Monthly
Steering: go or stop, 1 h
Ongoing
Decision log
Notes: Four deployment levels. In 12 weeks we go up to co-pilot: the team starts from the proposal and gives a reason for every change. Every disagreement with the tool is traced to its cause: missing rule, wrong rule, wrong data. Releasing a batch always stays the qualified person's decision. Governance: weekly 30-minute ops review, monthly one-hour steering committee that decides go or stop, a decision log read at every ritual. No surprises: bad news travels the same day, with options.

## Slide 6: To start Monday, we need 8 decisions
Decision | Who | When
Scope agreed: target, 4 projects, right to stop | CEO, sponsor | Monday
Sponsor: 30 min a week, blockers cleared in 1 week | Bruno Martel | Monday
Read-only access: ERP, production, LIMS, QMS | CIO | Day 1
IT security review started | CIO | Day 1
Baseline and gains protocol signed | Controller | W1
Order book and lost sales | Supply chain | W2
Named hours for experts | Sponsor, HR | W1–W4
Works council consulted | HR | Before W5
Notes: The sponsor gives 30 minutes a week and clears a blocker within a week. The IT security review starts on day one; meanwhile we work on exports. Experts' hours are freed by their managers, not asked of the experts. In France, the works council (CSE) is consulted before any tool that could monitor operators' work.